## Sheet1
PROJECT COLORED IMAGE
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（人日） | 优先级 | 如何演示 | 商业价值 | 理想时间（人日） | 复杂度 | 信息度 | 备注
1 | 1 | 1 | user story | 普通黑白图片上色 | 作为一个使用黑白图像上色的用户，我需要该程序能实现将我传入的黑白图片自动上色的功能，给我带来更好的视觉效果去观看多年的老照片 | Initial Feature | Not Done | 10 | 98 |  |  | 10
2 | 1 | 1 | user story | 根据个人意愿上色 | 作为一个使用黑白图像上色的用户，我需要该程序能实现根据个人意愿上色，选择一种色调，将图片以该颜色为主色调实现上色，可以根据我的想法将图片上成自己想要的颜色 | Initial Feature | Not Done | 5 | 96 |  |  | 5
3 | 1 | 1 | user story | 图像风格迁移 | 作为一个使用黑白图像上色的用户，我需要该程序能实现图像风格迁移，传入两张图片，一张黑白图像，一张想要的图像风格样片，将样片的图像风格迁移至黑白图像并上色 | Initial Feature | Not Done | 3 | 95 |  |  | 3
4 | 1 | 1 | user story | 前端代码优化 | 作为一个前端工作者，我需要实现前端的代码面向对象，以便我可以更好的修改出现的bug | Initial Feature | Not Done | 3 | 95 |  |  | 3
5 | 1 | 1 | user story | 后台管理 | 作为一个后台管理员，我需要及时控制用户的免费使用次数，以便我管理用户的权限得到保障 | Initial Feature | Not Done | 3 | 95 |  |  | 3
6 | 1 | 1 | user story | 后台控制 | 作为一个后台管理员，我需要拥有自己的内部账号，可以及时登录后台系统，以便可以及时控制该系统 | Initial Feature | Not Done | 3 | 95 |  |  | 3
7 | 1 | 1 | user story | 甲方使用权限 | 作为一个拥有黑白图像上色程序的企业，我需要有一个内部账号，拥有无限免费使用次数，方便自己的使用 | Initial Feature | Not Done | 2 | 80 |  |  | 2
8 | 1 | 1 | user story | 页面优化 | 作为一个使用黑白图像上色的用户，我需要网页更加便捷，给我带来更好的用户体验 | Initial Feature | Not Done | 2 | 95 |  |  | 2
9 | 1 | 1 | user story | 保护隐私权 | 作为一个使用黑白图像上色的用户，我需要别的用户不能看到我上传的照片，以便保护个人隐私 | Initial Feature | Not Done | 0.5 | 96 |  |  | 1
10 | 1 | 1 | user story | 用户体验 | 作为一个使用黑白图像上色的用户，我需要可以快速生成我想要的图片，给我带来更好的用户体验 | Initial Feature | Not Done | 1 | 95 |  |  | 1
Generate index cards
Note on A4: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B4: Luc Segers: This is the release where the story will be developped
Note on C4: Luc Segers: This is the sprint where the story will be developped
Note on D4: Luc Segers: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F4: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G4: Luc Segers: Type of the story.
Note on H4: Luc Segers: Status of the story
Note on I4: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on J4: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on L4: Luc Segers: 0 = Lowest Business Value 100 = Highest Business Value
Note on M4: Luc Segers: Enter here the new ideal estimates which are done with planningpoker
Note on N4: Luc Segers: Complexity 0 = Not Defined 1 = Very Simple 2 = Simple 3 = Moderate 4 = Complex 5 = Extreme Complex
Note on O4: Luc Segers: Information 0 = Not Defined 1 = No information 2 = Little information 3 = Moderate information 4 = Much information 5 = All information