## Sheet1
PROJECT BACKLOG
4 | = highest Reference ID number
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（h） | 优先级 | 如何演示 | 商业价值 | 理想时间（h） | 调整因子 | 复杂度 | 信息度 | 备注
1 | 1 | 1 | user story | 黑白照片彩色化 | 作为一个图像上色用户，我想要给黑白老照片上色，以便看看以前的年代的黑白照片变成彩色是什么样子。 | Initial Feature | Not Done | 385 | 98 | 上传黑白老照片，选择黑白照片上色，生成上色后的彩色照片。 |  | 350
2 | 1 | 1 | user story | 微信登录系统 | 作为一个图像上色用户，我想用微信登录自动上色系统，以便避免使用手机号或者邮箱登录带来的麻烦。 | Initial Feature | Not Done | 10 | 95 | 点击微信登录按钮，使用微信扫码登录，提示登录成功 |  | 10 | #REF!
3 | 1 | 1 | user story | 自定义上色 | 作为甲方,我希望自动上色系统能够实现用户可以自定义上色的功能，这样既可以实现自动上色，又可以实现根据用户喜好，自定义着色。 | Initial Feature | Not Done | 25 | 93 | 上传黑白老照片，选择自定义上色，通过提供的颜色自己操作着色 |  | 25
420
1 | 2 | 2 | user story | 黑白电影彩色化 | 作为甲方，我希望自动上色系统能实现给以前的黑白电影上色，以便吸引更多的用户。 | Initial Feature | Not Done | 365 | 98 | 上传一部以前的黑白老电影，选择黑白电影着色，生成一部上色后的电影（电影内容不变） |  | 330 | 0
2 | 2 | 2 | user story | 彩色电影在线观看 | 作为甲方，我希望实现彩色化的黑白电影，能够被用户在线观看，以便可以增加用户量。 | Initial Feature | Not Done | 20 | 90 | 用户登录后，选择一部已上色的电影，在线观看 |  | 20 | #REF!
3 | 2 | 2 | user story | 兼容其他主流app | 作为甲方，我希望能够实现与别的app的接口，以便获得更多的用户使用量。 | Initial Feature | Not Done | 25 | 91 | 选择一款已实现本系统接口的app，在此app上使用本系统进行上色 |  | 25
410
1 | 3 | 3 | user story | 草稿彩色化 | 作为甲方，我希望自动上色系统也能实现给草稿上颜色，以便增加系统的功能，吸引用户。 | Initial Feature | Not Done | 365 | 98 | 上传线稿，选择草稿上色按钮，显示上色后的结果 |  | 330 | #REF!
2 | 3 | 3 | user story | 用户评价 | 作为甲方，我希望能够得到用户对转换后的彩色图片（电影，草稿）的评价，以便了解系统的好坏。 | Initial Feature | Not Done | 20 | 92 | 点击评价，可对生成的结果写下自己的评价，其他用户可看到评价。 |  | 20 | #REF!
3 | 3 | 3 | user story | 下载生成结果至本地 | 作为一个使用本系统的用户，我希望能够将生成的彩色图片（电影，草稿）下载到本地，以便保存生成结果到本地。 | Initial Feature | Not Done | 10 | 93 | 上色完毕后，点击下载，可在相应的下载路径查看下载的彩色图片（电影，草稿） |  | 10
4 | 3 | 3 | user story | 分享生成结果 | 作为一个使用本系统的用户，我希望能将上色结果分享到其他平台，以便能和更多朋友分享。 | Initial Feature | Not Done | 15 | 88 | 点击分享，选择分享至..，可在相应位置查看已分享结果 |  | 15 | #REF!
410
Total |  | 10 | [5 empty] | 2070
Generate index cards
Note on A4: Luc Segers: This is the highest reference ID number used so far.
Note on A5: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B5: Luc Segers: This is the release where the story will be developped
Note on C5: Luc Segers: This is the sprint where the story will be developped
Note on D5: Luc Segers: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F5: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G5: Luc Segers: Type of the story.
Note on H5: Luc Segers: Status of the story
Note on I5: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on J5: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on L5: Luc Segers: 0 = Lowest Business Value 100 = Highest Business Value
Note on M5: Luc Segers: Enter here the new ideal estimates which are done with planningpoker
Note on N5: Luc Segers: This column is calculated based on the values of complexity and information. The data is looked up in the setup tab.
Note on O5: Luc Segers: Complexity 0 = Not Defined 1 = Very Simple 2 = Simple 3 = Moderate 4 = Complex 5 = Extreme Complex
Note on P5: Luc Segers: Information 0 = Not Defined 1 = No information 2 = Little information 3 = Moderate information 4 = Much information 5 = All information
Note on C19: Luc Segers: Total amount of stories available in the project backlog
Note on I19: Luc Segers: total amount of estimated hours